## operations
| id [-] | Logitic operation [-] | Time: value [h] | Time: function [-] | Time: other [-] | OLC: Hs [m] | OLC: Tp [s] | OLC: Ws [m/s] | OLC: Cs [m/s] | OLC: Other [-]
Mob | 100 | Mobilisation |  |  | vesselsDB['Mob time [h]']
AssPort | 101 | Assembly at port | 1
VessPrep | 102 | Vessel preparation & loading | 48
VessPrep_support | 103 | Vessel preparation & loading of individual support structures | 12
VessPrep_suction | 104 | Vessel preparation & loading of individual suction-embedment anchors | 4
VessPrep_pile | 105 | Vessel preparation & loading of individual pile anchors | 4
VessPrep_drag | 106 | Vessel preparation & loading of individual drag-embedment anchors | 4
VessPrep_direct | 107 | Vessel preparation & loading of individual direct-embedment anchors | 4
VessPrep_gravity | 108 | Vessel preparation & loading of individual gravity based foundations | 4
VessPrep_SeabedCP | 109 | Vessel preparation & loading of individual seabed collection points | 12
VessPrep_SurfaceCP | 110 | Vessel preparation & loading of individual surface piercing collection points | 48
VessPrep_driven | 111 | Vessel preparation & loading of individual driven piles | 4
VessPrep_external | 112 | Vessel preparation & loading of individual external protection equipment stacks | 4
TranPortSite | 113 | Transportation from port to site |  | transit_algorithm |  | vessel | vessel | vessel | vessel
TranSitePort | 114 | Transportation from site to port |  | transit_algorithm |  | vessel | vessel | vessel | vessel
TranSiteSite | 115 | Transportation from site to site |  | distance |  | vessel | vessel | vessel | vessel
Demob | 116 | Demobilisation |  |  | vesselsDB['Mob time [h]']
SeafloorEquipPrep | 117 | Seafloor & equipment preparation | 1 |  |  | vessel | 15 | 12.5 | 1.5
Grout | 118 | Grouting | 0.5 | grouting |  |  | 15 | 12.5 | 1.5
GroutRemov | 119 | Grouting equipment removal | 0.5 |  |  |  | 15 | 12.5 | 2
VesPos | 120 | Vessel Positioning | 6 |  |  | vessel | vessel | vessel | vessel
VesPosCables | 121 | Vessel Positioning | 1 |  |  | vessel | vessel | vessel | vessel
SuppStrutPos | 122 | Support structure positioning | 2 |  |  | vessel | vessel | vessel | vessel
LoadCableFactory | 200 | Loading cable from factory port |  | load_cable
OCT | 201 | Vessel Positioning + Connection to cable pull-head + Cable float-out + Cable lay into pre-excavated trench | 4.5 |  |  | 0.75 | 15 | 20 | 2.5
HDD | 202 | Vessel positioning + Connection to cable pull-head + Cable float-out + Cable pull-in through HDD conduit | 4.5 |  |  | 0.75 | 15 | 20 | 2.5
BurialToolDeploy | 203 | Deploy of Cable Burial Tool | 2 |  |  | 1.75 | 15 | 20 | 2
BurialToolRecov | 204 | Recover cable burial tool | 2 |  |  | 1.75 | 15 | 20 | 2
CableLay_Burial | 205 | Cable lay and burial through cable route |  | burial_time |  | 1.75 | 15 | 20 | 2
CableLay_Route | 206 | Cable lay through cable route |  | surface_time |  | 1.75 | 15 | 20 | 2
CableLay_Trench | 207 | Cable lay through open trench |  | surface_time |  | 1.75 | 15 | 20 | 2
CableLay_SplitPipe | 208 | Cable lay with split pipes |  | pipe_time |  | 1.75 | 15 | 20 | 2
CableLay_Dyn | 209 | Cable lay with buoyancy modules |  | surface_time |  | 1.75 | 15 | 20 | 2
Dry_Connect | 210 | Conduct dry-mate connection on deck | 0.5 |  |  | 2 | 15 | 20
Splice_Connect | 211 | Conduct splice connection on deck | 0.5 |  |  | 2 | 15 | 20
Wet_Connect | 212 | Connect to guide wire + Lower cable and connection equip + Perform wet-mate connect + Recover connection equip | 2 |  |  | 2.25 | 15 | 20 | 1
Jtube_Connect | 213 | J-tube entrance inspection + Guide wire connection + Cable lay + Cable pull + Cable connection | 2 |  |  | 2 | 15 | 20 | 2
Lower_Cable_Seabed | 214 | Lower cable-end to the seabed | 0.75 |  |  | 2 | 15 | 20 | 2.5
Lift_Cable_Seabed | 215 | Lift cable-end from seabed | 1.75 |  |  | 1.5 | 15 | 17 | 1.5
Lower_CP_Seabed | 216 | Lower collection point to the seabed | 2 |  |  | 2 | 15 | 17 | 1.5
Lift_Topside | 217 | Lift top-side platform | 5 |  |  | 2 | 15 | 15 | 2.5
Connect_Topside | 218 | Connect top-side platform to the support structure | 10 |  |  | 2 | 15 | 15 | 2.5
Install_mattress | 219 | Lift and overboard concrete mattress + Lower concrete mattress to seabed + Position and release concrete mattress + Recover installation frame | 0.5 |  |  | 2 | 15 | 15 | 2.5
Install_rockbag | 220 | Lift and overboard rock filter bag + Lower rock filter bag to seabed + Position and release concrete mattress | 0.5 |  |  | 2 | 15 | 15 | 2.5
Pre_SeaEquipPrep | 300 | Guiding template positioning + seafloor preparation equipment preparation | 2 |  |  |  | 15 | 12.5 | 1.5
Post_SeaEquipPrep | 301 | Seafloor preparation + support structure positioning and equipment preparation | 2 |  |  |  | 15 | 12.5 | 1.5
PileDrill | 302 | Driven pile foundation or anchor seafloor penetration through drilling rig + positioning |  | penetration_time |  |  | 15 | 12.5 | 1.5
PileHamm | 303 | Driven pile foundation or anchor seafloor penetration through hammering + positioning |  | penetration_time |  |  | 15 | 12.5 | 1.5
PileVibro | 304 | Driven pile foundation or anchor seafloor penetration through vibro-driving + positioning |  | penetration_time |  |  | 15 | 12.5 | 1.5
GBSpos | 305 | Gravity based foundation or anchor positioning | 1
GBSlow | 306 | Gravity based foundation or anchor lowering |  | lowering |  |  | 15 | 12.5 | 1.5
DragEmbed | 400 | Lowering mooring lines + Drag-embedment anchor seafloor penetration + Tensioning | 1.5 |  |  |  | 15 | 15 | 1.5
ConnectPile | 401 | Lowering mooring lines + Connecting end of mooring line to pre-installed pile + Tensioning | 0.5 |  |  |  | 15 | 12.5 | 1.5
CaissonSuct | 402 | Lowering anchors with mooring lines + Suction caisson anchor seafloor penetration + Tensioning |  | penetration_time
DirecSuct | 403 | Lowering anchors with mooring lines + Direct-embedment anchor seafloor penetration through suction-embedment + Tensioning |  | penetration_time |  |  | 15 | 20 | 1.5
DirecJet | 404 | Lowering anchors with mooring lines + Direct-embedment anchor seafloor penetration through jetting-embedment + Tensioning |  | penetration_time |  |  | 15 | 20 | 1.5
DirecMech | 405 | Lowering anchors with mooring lines + Direct-embedment anchor seafloor penetration through mechanical-embedment + Tensioning |  | penetration_time |  |  | 15 | 20 | 1.5
PreLay | 406 | Pre-lay moorings or buoy off | 0.5
DevAssPort | 500 | Device assembly at port |  |  | device['assembly duration [h]']
LoadOut_Lift | 501 | Load-out:Lifted away | 1
LoadOut_Skidded | 502 | Load-out:Skidded/Trailler | 2
LoadOut_Float | 503 | Load-out: Floated Away | 4
Seafast | 504 | Seafastening | 0.5
DeckTrans | 505 | Deck transportation |  | transit_algorithm |  | vessel | vessel | vessel | vessel
TowTrans | 506 | Towing transportation |  | transit_algorithm |  | vessel | vessel | vessel | vessel
PosBFdev | 507 | On-site posisitioning and connection of bottom-fixed device |  |  | device['connect duration [h]'] | device['max Hs [m]'] | device['max Tp [s]'] | device['max Ws [m/s]'] | device['max Cs [m/s]'] | end-user
PosFLTdev | 508 | On-site posisitioning and connection of floating device |  |  | device['connect duration [h]'] | device['max Hs [m]'] | device['max Tp [s]'] | device['max Ws [m/s]'] | device['max Cs [m/s]'] | end-user
Access | 600 | Access to the element |  |  | om['d_acc [hour]'] | om['Hs_acc [m]'] | om['Tp_acc [s]'] | om['Ws_acc [m/s]'] | om['Cs_acc [m/s]']
Maintenance | 601 | Inspection or Maintenance Operations |  |  | om['d_om [hour]'] | om['Hs_om [m]'] | om['Tp_om [s]'] | om['Ws_om [m/s]'] | om['Cs_om [m/s]']